## Sheet1
Task Name	Duration	Start	Finish	Predecessors	Resource Names
User Story Walk Through	1 day	Friday 19/1/24	Friday 19/1/24		Mubashir Abbas, Zaheer, Fazal, Abid, Mustafa
Design Document	2 days	Monday 22/1/24	Tuesday 23/1/24	2	Mubashir Abbas, Abid, Mustafa
Development	15 days	Wednesday 24/1/24	Tuesday 13/2/24	3	Abid, Mustafa
BA Review	1 day	Wednesday 14/2/24	Wednesday 14/2/24	4	Zaheer, Fazal
Code Review	1 day	Thursday 15/2/24	Thursday 15/2/24	5	Mubashir Abbas, Mubashir Hassan
QAT	1 day	Friday 16/2/24	Friday 16/2/24	6	Mubashir Abbas, Mubashir Hassan
UAT	1 day	Monday 19/2/24	Monday 19/2/24	7	Zaheer, Fazal
Project Closure	1 day	Tuesday 20/1/24	Tuesday 20/1/24	8	Abid, Mustafa